## Project Overview
ProfAI - Professor Exam Style Analysis Platform
PROJECT SUMMARY
ProfAI is a web application that allows university students to upload past exam papers and analyze the professor's question style. The system extracts question patterns from uploaded exam data and answers the question "How does this professor ask questions?". Built with React.js + Node.js + PostgreSQL technology stack.
TECHNOLOGY STACK
Layer | Technology | Version | Description | License
Frontend | React.js + TypeScript | 18.x | User interface | MIT
CSS Framework | Tailwind CSS | 3.x | Responsive design | MIT
Backend | Node.js + Express.js | 20.x | REST API server | MIT
Database | PostgreSQL | 15.x | Relational database | PostgreSQL License
ORM | Prisma | 5.x | Database management | Apache 2.0
File Upload | Multer | 1.x | Exam file upload handling | MIT
Container | Docker + Docker Compose | 24.x | Containerization | Apache 2.0

## Team Members & Roles
ProfAI - Team Members and Task Distribution
# | Full Name | Role | Responsibility Areas | Contact | Status
1 | ERDEM ACAR | Full-Stack Developer | User authentication (Auth), Professor & Course API endpoints, Dashboard page |  | Active
2 | ENES ALBAS | Full-Stack Developer | Exam upload system, Analysis engine, Exam API endpoints, Exam upload page |  | Active
3 | ALI EMIR ERTEN | Full-Stack Developer | Database design (Prisma), Rating system, Docker configuration, Professor detail page |  | Active
SHARED RESPONSIBILITIES (Everyone)
* Git version control and code review
* Unit test writing
* Documentation
* Jira task tracking

## Project Timeline
ProfAI - 8-Week Project Timeline
Week | Date Range | Phase | Tasks | Assignee | Deliverable
Week 1 | Week 1 | Planning & Setup | * Create project plan * Set up Jira board * Create Git repository * Configure Docker Compose * Set up development environment | Everyone | Project plan, Git repo, Docker setup
Week 2 | Week 2 | Database & Backend Foundation | * Design Prisma schema * Run database migrations * Set up Express.js project structure * Build Auth API (register/login) | Everyone | DB schema, Auth API
Week 3 | Week 3 | Backend API Development | * Professor API endpoints * Course API endpoints * Exam upload API (Multer) * Rating API endpoints | Everyone | All CRUD APIs
Week 4 | Week 4 | Analysis Engine & Frontend Foundation | * Exam analysis algorithm * React project setup * Tailwind CSS configuration * Routing structure (React Router) | Everyone | Analysis engine, Frontend skeleton
Week 5 | Week 5 | Frontend Pages - Part 1 | * Home page design * Registration/Login pages * Professor list page * API integration start | Everyone | 3 main pages
Week 6 | Week 6 | Frontend Pages - Part 2 | * Professor detail page * Analysis card (charts) * Exam upload page * Dashboard page | Everyone | All pages completed
Week 7 | Week 7 | Integration & Testing | * Frontend-Backend integration * Bug fixes * Responsive design check * Edge case testing | Everyone | Fully working application
Week 8 | Week 8 | Final Review & Submission | * Write README.md * Finalize UML diagrams * Code cleanup * Final push to GitHub * Share link on UBIS | Everyone | Final delivery
GANTT CHART
Task / Phase | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
Planning & Setup | bar: W1
Database Design | bar: W2
Backend API Development | bar: W2 to W3
Analysis Engine | bar: W4
Frontend Development | bar: W4 to W6
Integration | bar: W7
Testing & Bug Fixes | bar: W7
Documentation & Delivery | bar: W8

## Budget Planning
ProfAI - Budget Planning (Resources, Time, Members)
1. RESOURCE BUDGET (Tools & Technologies)
Resource | Type | Cost | Duration | Description
GitHub | Version Control | Free | 8 Weeks | Code storage and collaboration
Jira | Project Management | Free (Free Plan) | 8 Weeks | Task tracking and sprint management
VS Code | IDE | Free | 8 Weeks | Development environment
Docker Desktop | Container | Free (Personal) | 8 Weeks | Development and deployment environment
PostgreSQL | Database | Free (Open Source) | 8 Weeks | Data storage
Node.js | Runtime | Free (Open Source) | 8 Weeks | Backend runtime environment
draw.io | Diagram Tool | Free | 1 Week | UML diagrams
Google Meet | Communication | Free | 8 Weeks | Team meetings
Postman | API Testing | Free | 6 Weeks | API endpoint testing
TOTAL TOOL COST: |  |  | $0
2. TIME BUDGET (Person-Hours)
Phase | Duration (Weeks) | Hours/Person/Week | Total Person-Hours | Percentage (%)
Planning & Setup | 1 | 10 | 30 | 10%
Backend Development | 2 | 12 | 72 | 25%
Frontend Development | 3 | 12 | 108 | 35%
Integration & Testing | 1 | 15 | 45 | 15%
Documentation & Delivery | 1 | 15 | 45 | 15%
TOTAL: |  |  | 300 Person-Hours | 100%
3. MEMBER-BASED TIME DISTRIBUTION
Member | Weekly Hours | Total Hours (8 Weeks) | Primary Responsibility | Secondary Responsibility
ERDEM ACAR | 12-15 hours | ~100 hours | Auth, Professor/Course API, Dashboard | Code review, Testing
ENES ALBAS | 12-15 hours | ~100 hours | Exam upload, Analysis engine | Code review, Testing
ALI EMIR ERTEN | 12-15 hours | ~100 hours | DB design, Docker, Rating system | Code review, Testing

## Risk Analysis
ProfAI - Risk Analysis and Mitigation Strategies
# | Risk | Probability | Impact | Risk Level | Mitigation Strategy
R1 | Team member leaving or becoming unavailable | Low | High | MEDIUM | Cross-training among members. Documentation kept up to date. Knowledge sharing sessions.
R2 | Technology learning curve taking longer than expected | Medium | Medium | MEDIUM | Dedicate first week to research and tutorials. Use simpler alternatives if necessary.
R3 | Database design being insufficient | Low | High | MEDIUM | Prisma migration system allows easy schema changes. Early-stage design reviews planned.
R4 | Docker environment compatibility issues | Medium | Low | LOW | Docker Compose ensures standard dev environment. Local setup documented as fallback.
R5 | File upload security vulnerabilities | Medium | High | HIGH | File type and size validation. Uploaded files stored in separate directory. Multer validation applied.
R6 | API endpoint performance issues | Low | Medium | LOW | Pagination in database queries. Indexing applied where necessary.
R7 | Failure to meet project timeline | Medium | High | HIGH | Weekly Jira sprint reviews. Critical features prioritized. MVP approach adopted.
R8 | Git merge conflicts and code integration issues | High | Low | MEDIUM | Feature branch strategy. Small and frequent commits. Code review required for all PRs.
RISK MATRIX
| Low Impact | Medium Impact | High Impact
High Probability | MEDIUM (R8) | HIGH | HIGH
Medium Probability | LOW (R4) | MEDIUM (R2) | HIGH (R5, R7)
Low Probability | LOW (R6) | MEDIUM (R1, R3) | MEDIUM

## SWOT Analysis
ProfAI - SWOT Analysis
STRENGTHS | WEAKNESSES
+ Modern technology stack (React, Node.js, TypeScript) | - Small team (3 people) with limited workforce
+ Standardized development environment with Docker | - AI analysis is at MVP level (basic statistics)
+ Secure and easy database management with Prisma ORM | - Limited project duration (8 weeks)
+ All tools and technologies are open source and free | - Difficulty in collecting real exam data
+ All team members have Full-Stack competency | - Risk of low test coverage
+ Addresses a real need (student-focused platform) | - Time conflicts with team members' university courses
OPPORTUNITIES | THREATS
> AI integration for real NLP analysis in the future | ! Copyright issues (sharing exam questions)
> Platform potential to expand to all universities | ! GDPR/data privacy compliance requirements
> Mobile application version can be developed | ! Competition from similar platforms
> Collaboration with student communities possible | ! Risk of professors viewing platform negatively
> OCR integration for automatic question extraction | ! Server costs at deployment stage
> Professor self-management profile feature | ! Risk of fake/incorrect data uploads

## Communication Plan
ProfAI - Communication and Meeting Plan
COMMUNICATION CHANNELS
Channel | Purpose | Frequency | Participants | Tool
Daily Stand-up | Progress sharing, discuss blockers | Daily (15 min) | All team | Google Meet / WhatsApp
Sprint Planning | Weekly task planning | Weekly (Monday) | All team | Google Meet
Sprint Review | Weekly progress evaluation | Weekly (Friday) | All team | Google Meet
Code Review | Code quality control | Every PR | Min. 1 reviewer | GitHub PR
Emergency Contact | Critical bugs, blocker situations | As needed | Relevant members | WhatsApp / Phone
Documentation | Technical notes, decisions | Continuous | All team | GitHub Wiki / Notion
WEEKLY MEETING AGENDA
Order | Topic | Duration | Owner | Notes
1 | Review of the previous week | 10 min | Everyone | Each member shares their progress
2 | Demo of completed tasks | 15 min | Relevant member | Screen sharing demonstration
3 | Discussion of blockers and issues | 10 min | Everyone | Solution proposals determined
4 | Planning for the upcoming week | 10 min | Everyone | Jira board updated
5 | Task assignment and prioritization | 5 min | Everyone | Sprint backlog updated
REPORTING STRUCTURE
Report | Content | Frequency | Format | Distribution
Sprint Report | Completed/remaining tasks, issues | Weekly | Jira Sprint Report | Jira + Google Meet
Progress Report | Overall project status, % completion | Bi-weekly | Excel / Jira Dashboard | Presented to professor
Final Report | Full project summary, outputs, lessons | End of project | PDF / Word | UBIS